## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time
Group Number |  | 31
Participant 1 |  | Paul Renkel
Participant 2
Participant 3
Participant 4
Participant 5
Mentor |  | Andreas Schmidhofer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
I23-22 | As a player I want the map to have enemy spawns so that I can take part in the basic gameplay | 3 | 2 | -1 | 1 |  | Not spawnpoints, but spawn area
I23-4 | As a player I want to be able to use my weapon effectively | 1 | 1 | 0 | 1 |  | Part here was only for ui elements
I23-47 | As a player I want to have a meelee enemy | 1 | 1 | 0 | 1 |  | Animation of meelee attack previously didn't have to go through for hit to be applied
I23-17 | As a player I want to have waves of enemies spawning to give me targets | 3 | 1 | -2 | 1 |  | Only one enemy possible so far. Implementation doesnt yet account for potential other enemies.
I23-18 | As a player I want to have a score to keep track of my progress | 2 | 1 | -1 | 1
I23-19 | As a player I want to have a wave counter to know what wave I am in | 1 | 1 | 0 | 1
|  |  |  | -4 | 6 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol